## Sheet1
| September '25 |  |  |  |  | October '25 |  |  |  | November '25 |  |  |  | December '25 |  |  |  |  | Jan '25
| 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05
Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Project Planning | bar: 2025-09-01 to 2025-09-29
Project Selection | bar: 2025-09-01 to 2025-09-15
Learning Objectives | bar: 2025-09-01 to 2025-09-22
Project Formulation | bar: 2025-09-15 to 2025-09-29
Litterature Search | bar: 2025-09-01 to 2025-11-03
Depth Estimation Techniques | bar: 2025-09-01 to 2025-09-08
Monocular Depth Estimation | bar: 2025-09-08 to 2025-10-20
Object Recognition | bar: 2025-09-08 to 2025-10-27
Object Localisation | bar: 2025-09-15 to 2025-11-17
System Implementation | bar: 2025-09-15 to 2025-12-15
Monocular Depth Estimation | bar: 2025-09-01 to 2025-10-20
Object Recognition | bar: 2025-09-08 to 2025-10-27
Object Localisation | bar: 2025-09-29 to 2025-11-24
Pepper Implementation | bar: 2025-11-03 to 2025-12-22
Bachelor Report | bar: 2025-09-29 to 2026-01-05
Writing the report | bar: 2025-09-29 to 2025-12-29
Finishing and submitting | bar: 2026-01-05
[5 empty] | Overall time |  |  | Specified time |  |  | Flexible deadline |  |  | Deadline